## City of Boise Zoo
Caption: City of Boise Zoo ADA assessment findings, recommendations for remediation, and associated costs.
ID | LOCATION | BUILT BEFORE ADA | VIOLATIONS | 2010 ADA CODE | RECOMMENDATIONS | ESTIMATED COST | QUICK FIX | PRIORITY SCORE
3680 | Education Building Women’s Restroom | Yes | There is no tactile sign identifying the permanent room. | §216.2, §703 | Signs shall be Braille with raised lettering and should be placed on the wall in the center of an 18"x18" clear floor space.Install tactile signage on the latch side of the doorway at a height of 48” minimum to 60” maximum above the floor, identifying room by name or room number. | 100 | Yes | 3
2856 | Entrance Women’s Restroom | Yes | The clear floor space is obstructed by a door stop. | §305.2 | Remove the door stop from the sink's clear floor space. | 100 | Yes | 3
2391 | Jack and Esther Simplot Multipurpose Room | Yes | There is no tactile sign identifying the permanent room. | §216.2, §703 | Signs shall be Braille with raised lettering and should be placed on the wall in the center of an 18"x18" clear floor space.Install tactile signage to the right of the right hand door at a height of 48” minimum to 60” maximum above the floor, identifying room by name or room number. | 100 | Yes | 3
3748 | Men's Restroom by Condor Exhibit | Yes | There is no tactile sign identifying the permanent room. | §216.2, §703 | Signs shall be Braille with raised lettering and should be placed on the wall in the center of an 18"x18" clear floor space.Install tactile signage on the latch side of the doorway at a height of 48” minimum to 60” maximum above the floor, identifying room by name or room number. | 100 | Yes | 3
2388 | AED near Gift Shop Restroom | Yes | The AED protrudes 6.5" into the circulation space at 38" above the floor. | §307.2 | Recess the AED so it protrudes a maximum of 4" or place a cane detectable object beneath it. | 100 | Yes | 5
2870 | African Plains Exhibit Animal Presentation Area | Yes | The box protrudes 9" into the circulation space at 36" above the floor. | §307.2 | Recess the box so it protrudes a maximum of 4" or place a cane detectable object beneath it. | 100 | Yes | 5
2868 | African Plains Exhibit Travel Center | Yes | The lamp protrudes into the circulation space at 74" above the floor. | §307.2 | Raise it so the bottom edge is 80" maximum above the floor. | 100 | Yes | 5
2991 | African Plains Men's Restroom | Yes | The paper towel dispenser protrudes 10" into the circulation space at 42" above the floor. | §307.2 | Recess the paper towel dispenser so it protrudes a maximum of 4" or place a cane detectable object beneath it. | 100 | Yes | 5
2993 | African Plains Men's Restroom | Yes | The toilet paper dispenser is located out of the accessible reach range. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
2356 | Animal Care Staff Break/Office Area | Yes | The first aid box is outside of the unobstructed forward reach range at 52" above the floor.The first aid box protrudes 7" into the circulation space at 52" above the floor. | §307.2, §308.2.1 | Recess the first aid box so it protrudes a maximum of 4" or place a cane detectable object beneath it.Lower the first aid box by 4" to meet the accessible reach range of 15" minimum and 48" maximum above the floor. | 100 | Yes | 5
3334 | Animal Care Staff Break/Office Area Men’s Restroom | Yes | The toilet paper dispenser is located out of the accessible reach range. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
3397 | Animal Care Staff Break/Office Area Women's Restroom | Yes | The toilet paper dispenser is located out of the accessible reach range. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
3031 | Animal Health Complex | Yes | The electrical box protrudes 14" into the circulation space at 41" above the floor. | §307.2 | Place a cane detectable object beneath the electrical box. | 100 | Yes | 5
3731 | Animal Health Complex | Yes | The electric box protrudes 6.25" into the circulation space at 33.5" above the floor. | §307.2 | Place a cane detectable object beneath the electrical box. | 100 | Yes | 5
2353 | Animal Hospital | Yes | The eye wash station protrudes 12" into the circulation space at 12" above the floor. | §307.2 | Place a cane detectable object beneath the eye wash station. | 100 | Yes | 5
2362 | Education Building | Yes | The fire extinguisher protrudes 4.5" into the circulation space at 41" above the floor. | §307.2 | Recess the fire extinguisher so it protrudes a maximum of 4" or place a cane detectable object beneath it. | 100 | Yes | 5
2364 | Education Building | Yes | The paper towel dispenser is outside of the unobstructed forward reach range at 51" above the floor.The paper towel dispenser protrudes 51" into the circulation space at 8.5" above the floor. | §307.2, §308.2.1 | Recess the paper towel dispenser so it protrudes a maximum of 4" or place a cane detectable object beneath it.Lower the paper towel dispenser by 3" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 5
3667 | Education Building | Yes | The toilet paper dispenser is located out of the accessible reach range. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
3070 | Education Building Women’s Restroom | Yes | The toilet paper dispenser is located out of the accessible reach range. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
2857 | Entrance Women’s Restroom | Yes | The door to the accessible water closet is not self closing. Either self-closing hinges are not installed on the door or if installed, they are defective. | §604.8.1.2 | Install or reinstall self-closing hinges on the door to ensure that the door is self-closing per the ADA requirements. | 100 | Yes | 5
2861 | Entrance Women’s Restroom | Yes | The toilet paper dispenser is located out of the accessible reach range at 13" from the rim. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
2862 | Entrance Women’s Restroom | Yes | The dispenser is outside of the unobstructed forward reach range at 48.75" above the floor.The dispenser protrudes 6.75" into the circulation space at 48.75" above the floor. | §307.2, §308.2.1 | Recess the dispenser so it protrudes a maximum of 4" or place a cane detectable object beneath it.Lower the dispenser by 0.75" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 5
2863 | Entrance Women’s Restroom | Yes | The paper towel dispenser protrudes 8.5" into the circulation space at 38.5" above the floor. | §307.2 | Recess the paper towel dispenser so it protrudes a maximum of 4" or place a cane detectable object beneath it. | 100 | Yes | 5
3520 | EO Wilson Science and Exhibit Hall Women's Restroom | Yes | The toilet paper dispenser is located out of the accessible reach range at 5" in front of the rim. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
3521 | EO Wilson Science and Exhibit Hall Women's Restroom | Yes | The door to the accessible water closet is not self closing. Either self-closing hinges are not installed on the door or if installed, they are defective. | §604.8.1.2 | Install or reinstall self-closing hinges on the door to ensure that the door is self-closing per the ADA requirements. | 100 | Yes | 5
3329 | Friends of Zoo Boise Restroom | Yes | The door to the accessible water closet is not self closing. Either self-closing hinges are not installed on the door or if installed, they are defective. | §604.8.1.2 | Install or reinstall self-closing hinges on the door to ensure that the door is self-closing per the ADA requirements. | 100 | Yes | 5
3011 | Gift Shop Employee Restroom | Yes | The toilet paper dispenser is located out of the accessible reach range. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
3012 | Gift Shop Employee Restroom | Yes | The first aid box protrudes 9" into the circulation space. | §307.2 | Recess the first aid box so it protrudes a maximum of 4" or relocate it. | 100 | Yes | 5
3588 | Gift Shop Employee Restroom | Yes | The paper towel dispenser protrudes into the circulation space at 52" above the floor.The paper towel dispenser is outside of the unobstructed forward reach range at 52" above the floor. | §308.2.1, §307.2 | Lower the paper towel dispenser by 4" to meet the accessible reach range of 48" maximum above the floor.Recess the paper towel dispenser so it protrudes a maximum of 4" or place a cane detectable object beneath it. | 100 | Yes | 5
3083 | Kijiji Women’s Restroom | Yes | The door to the accessible water closet is not self closing. Either self-closing hinges are not installed on the door or if installed, they are defective. | §604.8.1.2 | Install or reinstall self-closing hinges on the door to ensure that the door is self-closing per the ADA requirements. | 100 | Yes | 5
3522 | Kijiji Women’s Restroom | Yes | The paper towel dispenser protrudes 8.5" into the circulation space at 43.5" above the floor. | §307.2 | Recess the paper towel dispenser so it protrudes a maximum of 4" or place a cane detectable object beneath it. | 100 | Yes | 5
2288 | Men's Restroom by Entrance | Yes | The toilet paper dispenser is located out of the accessible reach range at 16" in front of the toilet. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
2290 | Men's Restroom by Entrance | Yes | The door to the accessible water closet is not self closing. Either self-closing hinges are not installed on the door or if installed, they are defective. | §604.8.1.2 | Install or reinstall self-closing hinges on the door to ensure that the door is self-closing per the ADA requirements. | 100 | Yes | 5
3642 | Parque Nacional da Gorongosa African Wild Dog Viewing | Yes | The fire extinguisher protrudes 5" into the circulation space at 32" above the floor. | §307.2 | Recess the fire extinguisher so it protrudes a maximum of 4", lower it so the bottom edge is 27" maximum above the floor, or place a cane detectable object beneath it. | 100 | Yes | 5
3526 | Parque Nacional da Gorongosa EO Wilson Research Center | Yes | The TV protrudes 14.25" into the circulation space at 60" above the floor. | §307.2 | Recess the TV so it protrudes a maximum of 4", raise it so the bottom edge is 80" maximum above the floor, or place a cane detectable object beneath it. | 100 | Yes | 5
3630 | Parque Nacional da Gorongosa EO Wilson Research Center | Yes | The TV protrudes 12" into the circulation space at 60" above the floor. | §307.2 | Recess the TV so it protrudes a maximum of 4", raise it so the bottom edge is 80" maximum above the floor, or place a cane detectable object beneath it. | 100 | Yes | 5
3640 | Parque Nacional da Gorongosa Lion House | Yes | The TV protrudes 50" into the circulation space at 9.5" above the floor. | §307.2 | Recess the TV so it protrudes a maximum of 4", raise it so the bottom edge is 80" maximum above the floor, or place a cane detectable object beneath it. | 100 | Yes | 5
2877 | Sarus Crane | Yes | The box protrudes 6" into the circulation space at 54" above the floor. | §307.2 | Recess the box so it protrudes a maximum of 4", lower it so the bottom edge is 27" maximum above the floor, or place a cane detectable object beneath it. | 100 | Yes | 5
3564 | Zoo Kitchen Restroom | Yes | The toilet paper dispenser is located out of the accessible reach range behind the rim of the toilet. | §604.7 | The outlet of the dispenser shall be 15” minimum and 48” maximum above the floor and shall not be located behind the water closet.Remount the toilet paper dispenser to &nbsp;7” minimum and 9” maximum in front of the water closet measured to the centerline of the dispenser. | 100 | Yes | 5
2995 | African Plains Men's Restroom | Yes | The tactile sign identifying the room is not in the correct location at 62" above the floor. | §703.4 | Reinstall the sign on the latch side of the door at 48" minimum above the floor measured from the baseline of the lowest character and 60" maximum measured from the baseline of the highest character. | 100 | Yes | 6
3417 | African Plains Women’s Restroom | Yes | The tactile sign identifying the room is not in the correct location at 61" above the floor. | §703.4 | Reinstall the sign on the latch side of the door at 48" minimum above the floor measured from the baseline of the lowest character and 60" maximum measured from the baseline of the highest character. | 100 | Yes | 6
3333 | Animal Care Staff Break/Office Area Men’s Restroom | Yes | The tactile sign identifying the room is not in the correct location. | §703.4 | Reinstall the sign on the latch side of the door at 48" minimum above the floor measured from the baseline of the lowest character and 60" maximum measured from the baseline of the highest character. | 100 | Yes | 6
3393 | Animal Care Staff Break/Office Area Women's Restroom | Yes | The tactile sign identifying the room is not in the correct location. | §703.4 | Reinstall the sign on the latch side of the door at 48" minimum above the floor measured from the baseline of the lowest character and 60" maximum measured from the baseline of the highest character. | 100 | Yes | 6
2384 | Bench near Giraffe Slide | Yes | There is not a firm, stable, and slip resistant route to the bench. | §302.1, §305 | Relocate the bench adjacent to an accessible route. | 100 | Yes | 7
3663 | Education Building | Yes | The pipes under the sink are not covered. | §606.5 | Wrap the pipes beneath the sink with soft protective wrap or plastic. | 100 | Yes | 7
3664 | Education Building | Yes | The mirror is too high to be accessible at 48" above the floor. | §603.3 | Lower the mirror its bottom edge is a maximum height of 40" above the floor. | 100 | Yes | 7
3665 | Education Building | Yes | The faucet requires twisting of the wrist. | §309.4 | Replace the faucet with one that can be operated with a closed fist and without twisting the wrist. | 100 | Yes | 7
3168 | Kijiji Women’s Restroom | Yes | The pipes under the sink are not covered. | §606.5 | Wrap the pipes beneath the sink with soft protective wrap or plastic. | 100 | Yes | 7
3701 | Men's Restroom by Condor Exhibit | Yes | The faucet requires twisting of the wrist. | §309.4 | Replace the faucet with one that can be operated with a closed fist and without twisting the wrist. | 100 | Yes | 7
2286 | Men's Restroom by Entrance | Yes | There is no door handle on the inside of the stall door. | §309.4 | Add a door handle to allow users to pull open the door. Ensure that the handle can be operated with a closed fist and without twisting the wrist. | 100 | Yes | 7
2377 | Small Animal Kingdom (SAK) - Path Leaving Rain Forest | Yes | There is not a firm, stable, and slip resistant route to the trash can. | §302.1, §305 | Relocate the trash can adjacent to a level section of the accessible route. | 100 | Yes | 7
2381 | Small Animal Kingdom (SAK) - Trash Can near Rain Forest Pole | Yes | There is not a firm, stable, and slip resistant route to the trash can. | §302.1, §305 | Relocate the trash can adjacent to a level section of the accessible route. | 100 | Yes | 7
3560 | Zoo Kitchen Restroom | Yes | The mirror is too high to be accessible at 51" above the floor. | §603.3 | Lower the mirror its bottom edge is a maximum height of 40" above the floor. | 100 | Yes | 7
2357 | Animal Care/Staff Break Room | Yes | The paper towel dispenser is outside of the unobstructed forward reach range at 52" above the floor. | §308.2.1 | Lower the paper towel dispenser by 4" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 8
3666 | Education Building | Yes | The paper towel dispenser is outside of the unobstructed forward reach range at 52" above the floor. | §308.2.1 | Lower the paper towel dispenser by 4" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 8
3739 | Education Building Women’s Restroom | Yes | The paper towel dispenser is outside of the unobstructed forward reach range at 49.5" above the floor. | §308.2.1 | Lower the paper towel dispenser by 1.5" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 8
3429 | Friends of Zoo Boise Kitchen | Yes | The paper towel dispenser is outside of the unobstructed forward reach range at 53" above the floor. | §308.2.1 | Lower the paper towel dispenser by 5" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 8
3327 | Friends of Zoo Boise Restroom | Yes | The paper towel dispenser is outside of the unobstructed forward reach range at 51" above the floor. | §308.2.1 | Lower the paper towel dispenser by 3" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 8
3102 | Giraffe Slide | Yes | The hand sanitizer dispenser is outside of the unobstructed forward reach range at 53" above the floor. | §308.2.1 | Lower the hand sanitizer dispenser by 5" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 8
2287 | Men's Restroom by Entrance | Yes | The hook is outside of the unobstructed forward reach range at 68" above the floor. | §308.2.1 | Lower the hook by 20" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 8
3561 | Zoo Kitchen Restroom | Yes | The paper towel dispenser is outside of the unobstructed forward reach range at 50" above the floor. | §308.2.1 | Lower the paper towel dispenser by 2" to meet the accessible reach range of 48" maximum above the floor. | 100 | Yes | 8
2284 | Men's Restroom by Entrance | Yes | There is not adequate maneuvering clearance to operate the door due to the paper towel dispenser protruding 10" into the circulation space. | §307.2, §404.2.4.1 | Ensure that the paper towel dispenser does not protrude more than 4" into the restroom.Relocate the paper towel dispenser so that there is a clear floor space extending 18" from the latch side of the door, for a depth of 60" perpendicular from the doorway. | 200 | Yes | 4
3565 | Zoo Kitchen Restroom | Yes | The shelves protrude 12" into the circulation space. | §307.2 | Remove the shelves. | 200 | Yes | 5
2994 | African Plains Men's Restroom | Yes | The faucets require twisting of the wrist. | §309.4 | Replace the faucets with a lever handles that can be operated with a closed fist and without twisting the wrist. | 200 | Yes | 7
3737 | Education Building Women’s Restroom | Yes | The pipes under the sinks are not covered. | §606.5 | Wrap the pipes beneath the sinks with soft protective wrap or plastic. | 200 | Yes | 7
3738 | Education Building Women’s Restroom | Yes | The mirrors are too high to be accessible at 46" above the floor. | §603.3 | Lower the mirrors so its bottom edge is a maximum height of 40" above the floor. | 200 | Yes | 7
2864 | Entrance Women’s Restroom | Yes | The pipes under the sinks are not covered. | §606.5 | Wrap the pipes beneath the sinks with soft protective wrap or plastic. | 200 | Yes | 7
2865 | Entrance Women’s Restroom | Yes | The mirrors are too high to be accessible at 41" above the floor. | §603.3 | Lower the mirrors so their bottom edges are a maximum height of 40" above the floor. | 200 | Yes | 7
3353 | Men's Restroom by Condor Exhibit | Yes | The pipes under the sinks are not covered. | §606.5 | Wrap the pipes beneath the sinks with soft protective wrap or plastic. | 200 | Yes | 7
3437 | Men's Restroom by Condor Exhibit | Yes | The mirrors are too high to be accessible at 46" above the floor. | §603.3 | Lower the mirrors so its bottom edge is a maximum height of 40" above the floor. | 200 | Yes | 7
3587 | Main Entrance Parking | Yes | The parking signs identifying the accessible parking space do not meet the minimum height requirement of 60" from the ground. | §216.5 | Remount the accessible parking signs to ensure 60" minimum height from the ground. | 200 | Yes | 9
3579 | Main Entrance Parking Gate 10 | Yes | Two parking signs identifying the accessible parking spaces do not meet the minimum height requirement of 60" above the ground. | §502.6 | Reinstall the accessible parking signs at each accessible space at a minimum height of 60" above the ground. | 200 | Yes | 9
3654 | Entire Facility | Yes | Benches throughout the zoo do not provide back support. Benches are located at the Giraffe viewing area, main entrance gate 1,central paving entry bridge, Serval Cat viewing, EO Wilson Science and Exhibit Hall in Gorongosa National Park, and the Education Building. | §903.4 | For the purposes of achieving greater accessibility and Human Centric Design, consider dispersing benches with back support throughout the zoo. | 500 | Yes | 0
2866 | Entrance Drinking Fountains | Yes | The drinking fountains protrude 19" into the circulation path. | §602, §307.2 | Place a drinking fountain skirt at this location to provide cane detectability. | 500 | Yes | 10
3106 | Animal Care Staff Break/Office Area Ramp to Lunch Area | Yes | There is a 1" in the pathway posing a tripping hazard. | §302.3 | Fill in the gap to reduce the gap to a maximum of 0.5". | 500 | Yes | 3
3130 | Farm Animals Exhibit | Yes | There is a change in level that pose tripping hazards in the accessible route. | §302.1 | Repave the area of the sidewalk to remove the change in level. | 500 | Yes | 3
3114 | Parque Nacional da Gorongosa Nyala | Yes | The change in level between 0.25" and 0.5" is not beveled. | §303.3 | Bevel the change in level with a slope not steeper than 1:2. | 500 | Yes | 3
3043 | Entire Facility | Yes | There is no clear floor space next to most of the benches throughout the zoo. | §903.2 | For the purposes of achieving greater accessibility and Human Centric Design, install a 30"x48" clear floor space at the end of the bench seat and parallel to the short axis of the bench or relocate the benches on the accessible route.</div | 500 | Yes | 5
3328 | Friends of Zoo Boise Restroom | Yes | The side grab bar extends 49" from the rear wall. | §604.5.1 | Remount the side grab bar 12" maximum from the rear wall and extending 54" minimum from the rear wall. | 500 | Yes | 5
3079 | Carousel | Yes | The clear floor space in front of the bench is 24"x30". | §305.2 | Rearrange the carousel seats to allow for a minimum clear floor space at the bench of 30"x48". | 500 | Yes | 7
2890 | Soala Viewing | Yes | There is not a level landing at the top of the ramp. | §405.7 | Install a level landing at the top of the ramp. Landings shall be as wide as the widest ramp run leading to the landing and 60" long minimum. | 1000 | No | 1
3533 | Animal Care Staff Break/Office Area Ramp to Lunch Area | Yes | The cross slope is 3.1%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
3725 | Capybara | Yes | The clear floor space has a 2.6% cross slope and 4.5% running slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 3
3021 | Eagle Viewing | Yes | The clear floor space has a 4% running slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 3
2891 | Entrance | Yes | There are open grates in the pathway posing a tripping hazard. | §302.3 | Replace the grate with one that has gaps that are a maximum of 0.5”. | 1000 | No | 3
3212 | Farm Animals Exhibit | Yes | The cross slope is 4%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
3342 | Giraffes Viewing | Yes | The clear floor space has a 2.6% to 2.7% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 3
3308 | Greater Rhea Exhibit | Yes | The cross slope is 3%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
2390 | Jack and Esther Simplot Multipurpose Room | Yes | The entrance has a 3.1% slope. | §404.2.4.4 | Resurface the entryway to reduce the running slope to a maximum of 2% in all directions for a distance of 60" perpendicular to the doorway. | 1000 | No | 3
3586 | Main Entrance Parking | Yes | One of the accessible parking space is not of sufficient width at 88" wide. | §502.2 | Expand the accessible parking space to a minimum of 96" wide. | 1000 | No | 3
3457 | Orangutan Path | Yes | The cross slope is 2.5%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
3709 | Parakeet Pathway | Yes | There are tripping hazards in the accessible route causing changes in level. | §302.1 | Repave the area of the sidewalk to remove the bump. | 1000 | No | 3
3379 | Parque Nacional da Gorongosa African Wild Dog Viewing | Yes | The clear floor space at the right viewing window has a 2.5% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 3
3593 | Parque Nacional da Gorongosa Chitengo Camp | Yes | The cross slope is 2.6%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
3361 | Parque Nacional da Gorongosa Zebra | Yes | The clear floor space at the Zebra viewing has a 3% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 3
2371 | Path to Climbing Statues | Yes | The running slope reaches 6.2%. | §403.3 | Resurface the route to reduce the running slope to a maximum of 5%. | 1000 | No | 3
3172 | Prairie Dog Exhibit | Yes | The cross slope is 3%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
3524 | Ramp to Bear Viewing | Yes | The turning space has a 2.8% slope. | §304.2 | Resurface the turning space to reduce the slope to the maximum allowable 2% in all directions. | 1000 | No | 3
3236 | Red Panda Exhibit Class Area | Yes | The provided picnic tables do not have an accessible clear space for a wheelchair user. | §226.1, §902, §305, §306 | Ensure that the wheelchair accessible seating has a clear floor space of 30" x 48" with a slope not steeper than 2% and that the tables have sufficient knee and toe clearance.Add/replace picnic tables so that at least 5% of the seating is wheelchair accessible. | 1000 | No | 3
3252 | Red Panda Play Area | Yes | The turning space has a 4% slope. | §304.2 | Resurface the turning space to reduce the slope to the maximum allowable 2% in all directions. | 1000 | No | 3
2329 | Serval Cat | Yes | The cross slope is 4%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
2383 | Small Animal Kingdom (SAK) | Yes | The running slope is 8.2%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5% or 8.3% slope with level landings and handrails. | 1000 | No | 3
3420 | Small Animal Kingdom (SAK) | Yes | The running slope is 5.1%. | §403.3 | Resurface the route to reduce the running slope to a maximum of 5%. | 1000 | No | 3
2374 | Small Animal Kingdom (SAK) - Path Leaving Tiger Area | Yes | The cross slope reaches 2.6%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
2378 | Small Animal Kingdom (SAK) - Rain Forest Exit | Yes | The running slope reaches 6.3%. | §403.3 | Resurface the route to reduce the running slope to a maximum of 5%. | 1000 | No | 3
3724 | Small Animal Kingdom (SAK) Green Tree Python | Yes | The clear floor space at the Green Tree Python viewing has a 3% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 3
3525 | Small Animal Kingdom (SAK) New Animal Exhibit | Yes | The clear floor space at the New Animal Exhibit viewing has a 3% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 3
3536 | Small Animal Kingdom (SAK) Rainforest Exit/Tiger Exhibit | Yes | The cross slope is 2.4%. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 1000 | No | 3
2883 | Stage | Yes | There is no level landing provided at the bottom of the ramp. | §406.4 | Install a level landing at the bottom of the ramp with a minimum clear length of 36" and a slope no greater than 2% in all directions. | 1000 | No | 3
3082 | Tiger Exhibit | Yes | The clear floor space at the Tiger viewing has a 2.9% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 3
3405 | Tiger Exhibit | Yes | There is a change in level that pose tripping hazards in the accessible route. | §302.1 | Repave the area of the sidewalk to remove the change in level. | 1000 | No | 3
3452 | Kijiji Cafe | Yes | The counter is 37" above the ground. | §904.4.1 | A portion of the service counter must be no higher than 36" above the ground for a horizontal distance of 36". | 1000 | No | 4
3634 | Zoo Kitchen Employee Only Entrance | Yes | There is not adequate maneuvering clearance to operate the door. | §404.2.4.1 | Change the direction that the door swings or expand the area for which the door opens by removing obstructions to provide adequate maneuvering clearance to allow for a minimum of 48" to the latch side of the door. | 1000 | No | 4
2992 | African Plains Men's Restroom | Yes | The accessible water closet does not have a vertical grab bar. | ICC A117.1 §604.5.1 | The centerline of the vertical grab bar shall be located 39" minimum and 41" maximum from the real wall.Install an 18" long (minimum) vertical grab bar on the side wall. The grab bar shall be mounted with the bottom located at 39" minimum and 41" maximum above the floor. | 1000 | No | 5
3335 | Animal Care Staff Break/Office Area Men’s Restroom | Yes | The accessible water closet does not have a vertical grab bar. | ICC A117.1 §604.5.1 | The centerline of the vertical grab bar shall be located 39" minimum and 41" maximum from the real wall.Install an 18" long (minimum) vertical grab bar on the side wall. The grab bar shall be mounted with the bottom located at 39" minimum and 41" maximum above the floor. | 1000 | No | 5
3394 | Animal Care Staff Break/Office Area Women's Restroom | Yes | The flush control is located on the wall side of the toilet. | §604.6 | Either make the toilet flush automatically or relocate the flush control to be operated on the open side of the toilet. | 1000 | No | 5
3395 | Animal Care Staff Break/Office Area Women's Restroom | Yes | The accessible water closet does not have a vertical grab bar. | ICC A117.1 §604.5.1 | The centerline of the vertical grab bar shall be located 39" minimum and 41" maximum from the rear wall.Install an 18" long (minimum) vertical grab bar on the side wall. The grab bar shall be mounted with the bottom located at 39" minimum and 41" maximum above the floor. | 1000 | No | 5
3396 | Animal Care Staff Break/Office Area Women's Restroom | Yes | The side grab bar is located 2" from the rear wall. | §604.5.1 | Replace the side grab bar with one that is a minimum of 42" long minimum, located 12" maximum from the rear wall and extending 54" minimum from the rear wall. | 1000 | No | 5
2358 | Animal Care/Staff Break Room | Yes | There is no knee clearance underneath the sink.The sink is 34.25" above the floor. | §606.3, §306.3.3 | Lower the sink to the maximum height of 34" above the floor.Provide knee clearance underneath the counter at the sink that is a minimum of 11" deep at 9" above the floor and 8" deep at 27" above the floor. | 1000 | No | 5
3508 | Conservation Cruise | Yes | There is a change in level greater than 0.25". | §303.2 | Resurface the pathway to reduce the change in level to less than 0.25" or 0.5" if beveled. | 1000 | No | 5
3661 | Education Building | Yes | The flush control is located on the wall side of the toilet. | §604.6 | Either make the toilet flush automatically or relocate the flush control to be operated on the open side of the toilet. | 1000 | No | 5
2860 | Entrance Women’s Restroom | Yes | The centerline of the toilet is located 19" from the sidewall. | §604.2 | Reposition the centerline of the toilet to be within 16" minimum and 18" maximum from the sidewall. | 1000 | No | 5
4490 | Entrance Women’s Restroom | Yes | The accessible water closet does not have a vertical grab bar. | ICC A117.1 §604.5.1 | The centerline of the vertical grab bar shall be located 39" minimum and 41" maximum from the rear wall.Install an 18" long (minimum) vertical grab bar on the side wall. The grab bar shall be mounted with the bottom located at 39" minimum and 41" maximum above the floor. | 1000 | No | 5
4491 | Entrance Women’s Restroom | Yes | The flush control is located on the wall side of the toilet. | §604.6 | Either make the toilet flush automatically or relocate the flush control to be operated on the open side of the toilet. | 1000 | No | 5
3519 | EO Wilson Science and Exhibit Hall Women's Restroom | Yes | The centerline of the toilet is located 18.5" from the sidewall. | §604.2 | Reposition the centerline of the toilet to be within 16" minimum and 18" maximum from the sidewall. | 1000 | No | 5
2351 | FOZB (Friends of Zoo Boise) | Yes | Handrails are not located at a compliant height above the stair nosings. | §505.4 | Lower the handrails to a minimum height of 34" and a maximum of 38" above the stair nosings. Ensure that the handrails are at a consistent height along the stair treads. | 1000 | No | 5
3419 | Gift Shop Employee Restroom | Yes | The flush control is located on the wall side of the toilet. | §604.6 | Either make the toilet flush automatically or relocate the flush control to be operated on the open side of the toilet. | 1000 | No | 5
2389 | Jack and Esther Simplot Multipurpose Room | Yes | There is no knee clearance underneath the sink. | §306.3.3 | Provide knee clearance underneath the counter at the sink that is a minimum of 11" deep at 9" above the floor and 8" deep at 27" above the floor. | 1000 | No | 5
2334 | Kajiji Kitchen | Yes | The sink is 35" above the floor. | §606.3 | Lower the sink to the maximum height of 34" above the floor. | 1000 | No | 5
3736 | Kijiji Cafe | Yes | There is a 1" change in level. | §303.2 | Resurface the pathway to reduce the change in level to a maximum of 0.25" or 0.5" if beveled. | 1000 | No | 5
3086 | Kijiji Women’s Restroom | Yes | The accessible water closet does not have a vertical grab bar. | ICC A117.1 §604.5.1 | The centerline of the vertical grab bar shall be located 39" minimum and 41" maximum from the rear wall.Install an 18" long (minimum) vertical grab bar on the side wall. The grab bar shall be mounted with the bottom located at 39" minimum and 41" maximum above the floor. | 1000 | No | 5
3689 | Men's Restroom by Condor Exhibit | Yes | The urinal is 24" above the floor. | §605.2 | Lower one urinal so its rim is a maximum of 17" above the floor. | 1000 | No | 5
2285 | Men's Restroom by Entrance | Yes | The urinal is 19" above the floor. | §605.2 | Lower the urinal to a maximum height of 17" above the floor. | 1000 | No | 5
2289 | Men's Restroom by Entrance | Yes | The accessible water closet does not have a vertical grab bar. | ICC A117.1 §604.5.1 | The centerline of the vertical grab bar shall be located 39" minimum and 41" maximum from the rear wall.Install an 18" long (minimum) vertical grab bar on the side wall. The grab bar shall be mounted with the bottom located at 39" minimum and 41" maximum above the floor. | 1000 | No | 5
3385 | Parque Nacional da Gorongosa EO Wilson Research Center | Yes | There are no handrail extensions for the ramp. | §505.10 | Extend the ramp handrails 12” horizontally beyond the top and bottom of ramp runs. | 1000 | No | 5
2999 | Parque Nacional da Gorongosa Zebra | Yes | There is a change in level greater than 0.25". | §303.2 | Resurface the pathway to reduce the change in level to a maximum of 0.25" or 0.5" if beveled. | 1000 | No | 5
2373 | Small Animal Kingdom (SAK) - Path Leading Zoo Farm | Yes | There is a 1.5" change in level. | §303.2 | Resurface the pathway to reduce the change in level to less than 0.25" or 0.5" if beveled. | 1000 | No | 5
2379 | Small Animal Kingdom (SAK) - Rain Forest Exit | Yes | There is a 2" change in level. | §303.2 | Resurface the pathway to reduce the change in level to less than 0.25" or 0.5" if beveled. | 1000 | No | 5
3030 | South American Loop | Yes | There is a 1" change in level. | §303.2 | Resurface the pathway to reduce the change in level to less than 0.25" or 0.5" if beveled. | 1000 | No | 5
3408 | South American Loop Capybara to Penguin Pavilion | Yes | There are no handrail extensions for the ramp. | §505.10 | Extend the ramp handrails 12” horizontally beyond the top and bottom of ramp runs. | 1000 | No | 5
2386 | Stairs Across from Gift Shop | Yes | There are no handrail extensions at the top and bottom of the stairs. | §505.10.2, §505.10.3 | Handrail extensions shall return the wall, guard or landing surface, or shall be continuous to the handrail of an adjacent stair flight.Install new handrails that have extensions at the slope of the stair flight for a horizontal distance at least equal to one tread depth beyond the last riser nosing. | 1000 | No | 5
2370 | Stairs to Amphitheater | Yes | There are no handrail extensions at the top of the stairs. | §505.10.2 | Install new handrails with extensions that extend at least 12" horizontally above the landing beginning directly above the first stair riser nosing. | 1000 | No | 5
3534 | Tiger Exhibit | Yes | The paw prints cause a 0.75" change in level. | §303.2 | Resurface the paw prints so that they are a maximum of 0.25" deep. | 1000 | No | 5
2359 | Zoo Kitchen | Yes | The sink is 39" above the floor. | §606.3 | Although not a public use area, should an employee with a disability request it, a sink and counter no higher than 34" should be provided. | 1000 | No | 5
3562 | Zoo Kitchen Restroom | Yes | The flush control is located on the wall side of the toilet. | §604.6 | Either make the toilet flush automatically or relocate the flush control to be operated on the open side of the toilet. | 1000 | No | 5
3563 | Zoo Kitchen Restroom | Yes | The rear grab bar is centered to the toilet. | §604.5.2 | Replace the rear grab bar with one that is a minimum of 36" long minimum and extends from the centerline of the water closet 12" minimum on one side and 24" minimum on the other. | 1000 | No | 5
3438 | Conservation Cruise | Yes | There are no handrails provided for boat loading/unloading. | §505.2 | Make sure there are adequate handrail extensions both at the top and bottom of the handrail.Install handrails for boat loading/unloading at a minimum height of 34” and maximum of 38” above the ground. | 1000 | No | 6
2875 | Soala Viewing | Yes | There are no handrails. | §505.2 | Install handrails at a minimum height of 34” and maximum of 38” above the ground. Make sure there are adequate handrail extensions both at the top and bottom of the handrail. | 1000 | No | 6
2366 | Stairs near Bear Viewing | Yes | There is a handrail on one side of the stairs. | §505.2 | Install an additional handrail at a minimum height of 34” and maximum of 38” above the ground. Make sure there are adequate handrail extensions both at the top and bottom of the handrail. | 1000 | No | 6
3481 | Farm Animals Exhibit Food Dispenser Machines | Yes | The clear floor space has a 3.1% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
3537 | Parque Nacional da Gorongosa Crocodiles | Yes | The clear floor space has a 2.5% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
3658 | Parque Nacional da Gorongosa EO Wilson Research Center | Yes | The clear floor space at the informational sign has a 3% cross slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
2375 | Small Animal Kingdom (SAK) - Path Leaving Rain Forest | Yes | The clear floor space has a 2.5% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
3199 | Small Animal Kingdom (SAK) Rainforest Exit/Tiger Exhibit | Yes | There is not a firm, stable, and slip resistant route to the play feature. | §302.1, §305 | Replace the mulch with an accessible playground surface material such as pour-in-place rubber, rubber tiles, artificial grass, or engineered wood fiber. | 1000 | No | 7
2885 | Snow Leopard Garbage Can | Yes | The clear floor space has a 3.5% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
2886 | Snow Leopard Garbage Can | Yes | The clear floor space has a 2.8% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
3319 | Tiger Exhibit | Yes | The clear floor space has a 2.4% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
2385 | Trash Can near Giraffe Slide | Yes | The clear floor space to the trash cans has a 3.5% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
2339 | Trash Cans at Grevy's Zebra | Yes | The clear floor space to the trash cans has a 3.8% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
2368 | Trash Cans to Bear Viewing | Yes | The clear floor space has a 2.8% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 1000 | No | 7
2871 | African Plains Exhibit Animal Presentation Area | Yes | There is not a firm, stable, and slip resistant route to the benches.The benches do not have back support. | §903.4, §302.1, §305 | For the purposes of achieving greater accessibility and Human Centric Design, consider installing back support to some of the benches.Construct a firm, stable, and slip resistant accessible route with a maximum cross slope of 2% and maximum running slope of 5%. | 1000 | No | 8
3703 | African School House | Yes | There are no wheelchair spaces at the desks in the African School House. | §221.2.1.1 | Ensure that there is knee clearance at a minimum of 11" deep at 9" above the floor and 8" deep at 27" above the floor.Provide one wheelchair space at one of the three desks by removing a 36" portion of the bench from the end of the desk. | 1000 | No | 8
2348 | Bench Across from Zoo Kitchen | Yes | There is no clear floor space next to the bench. | §903.2 | For the purposes of achieving greater accessibility and Human Centric Design, install a 30"x48" clear floor space at the end of the bench seat and parallel to the short axis of the bench. | 1000 | No | 8
3430 | Friends of Zoo Boise Kitchen | Yes | The dining and work surface counter is 34.5" above the floor. The sink is 34.5" above the floor.There is no knee clearance underneath the sink. | §306.3.3, §606.3, §902.3 | Provide knee clearance underneath the counter at the sink that is a minimum of 11" deep at 9" above the floor and 8" deep at 27" above the floor.A 30" portion of the dining and work surface must be no higher than 34” above the floor. Lower the sink to the maximum height of 34" above the floor. | 1000 | No | 8
3596 | South American Loop Penguin Pavilion | Yes | The sink and work surface counter is 35" above the floor. | §902.3 | Although not a public use area, should an employee with a disability request it, a sink and counter no higher than 34" should be provided. | 1000 | No | 8
3281 | Main Entrance Parking Crosswalk | Yes | The crosswalk paint is fading. | General Guidance | For the purposes of achieving greater accessibility and Human Centric Design, restripe the crosswalk to make it more visible to motorists. | 1000 | No | 9
3740 | Kijiji Women’s Restroom | Yes | The drinking fountains protrude 18" into the circulation path.The height of the tall drinking fountain is not compliant with a spout height of 36.75" above the ground. | §602.4, §602.7, §602, §307.2 | Raise the existing tall drinking fountain in order to comply with the 38" minimum spout height above the ground.Place drinking fountain skirts at this location to provide cane detectability. | 1500 | No | 6
3357 | Parque Nacional da Gorongosa Bats | Yes | The clear floor space at the viewing windows have 2.8% and 2.6% slopes. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2000 | No | 3
3612 | Parque Nacional da Gorongosa Warthog | Yes | The clear floor space has a 3.1% slope at the middle window and 2.3% at the side window. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2000 | No | 3
3155 | Education Building | Yes | There are no handrail extensions at the bottom of the stairs. | §505.10.2, §505.10.3 | Handrail extensions shall return the wall, guard or landing surface, or shall be continuous to the handrail of an adjacent stair flight.Install new handrails that have extensions at the slope of the stair flight for a horizontal distance at least equal to one tread depth beyond the last riser nosing. | 2000 | No | 5
3073 | Friends of Zoo Boise Wooden Ramp | Yes | The handrail extensions are 10". | §505.10.1 | Install new handrails that have handrail extensions that either return to a wall, guard, or the landing surface which extend at least 12" beyond the ramp run. | 2000 | No | 5
3386 | Parque Nacional da Gorongosa EO Wilson Research Center | Yes | Handrails are not located at a compliant height above the stair nosings at 39.5" above the stair nosings. | §505.4 | Lower the handrails to a minimum height of 34" and a maximum of 38" above the stair nosings. Ensure that the handrails are at a consistent height along the stair treads. | 2000 | No | 5
2884 | Stage | Yes | The handrails extend 9" at the top above the ramp run and stairwell. | §505.10.1 | Install new handrails that have handrail extensions that either return to a wall, guard, or the landing surface which extend at least 12" beyond the ramp run and stairwell. | 2000 | No | 5
2369 | Stairs to Amphitheater | Yes | Handrails are not located at a compliant height above the stair nosings. | §505.4 | Lower the handrails to a minimum height of 34" and a maximum of 38" above the stair nosings. Ensure that the handrails are at a consistent height along the stair treads. | 2000 | No | 5
2888 | Soala Viewing | Yes | There are no handrails. | §505.2 | Install handrails at a minimum height of 34” and maximum of 38” above the ground. Make sure there are adequate handrail extensions both at the top and bottom of the handrail. | 2000 | No | 6
2880 | Seating Area | Yes | The clear floor space has a 4.1% slope. | §305.2 | Resurface the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2000 | No | 7
2392 | Ticket Booth | Yes | The door knob requires twisting of the wrist.The elevated component is only accessible via a step. | §405, §309.4 | If requested by an employee with a disability, add a ramp with a slope not exceeding 8.3% with handrails. Ensure that a level landing is placed at the top of the ramp to allow for the maneuvering clearance at the doorway.Replace the door knob with a lever handle that can be operated with a closed fist and without twisting the wrist. | 2000 | No | 7
2869 | African Plains Exhibit Travel Center | Yes | The photo booth is only accessible via a 7" step. | §405 | Add vertical access to the photo booth by installing a ramp. Ensure that the slope does not exceed 8.3%, handrails are provided, and there is sufficient room for a level landing at the top and bottom of the ramp. | 2000 | No | 8
2352 | Animal Hospital | Yes | The sink is 34.25" above the floor. The dining and work surface counter is 34.25" above the floor.There is no knee clearance underneath the sink. | §306.3.3, §902.3, §606.3 | Provide knee clearance underneath the counter at the sink that is a minimum of 11" deep at 9" above the floor and 8" deep at 27" above the floor.Lower the sink to the maximum height of 34" above the floor. | 2000 | No | 8
2363 | Education Building | Yes | The sink is 36" above the floor. There is no knee clearance underneath the sink.The dining and work surface counter is 36" above the floor. | §902.3, §306.3.3, §606.3 | A 30" portion of the dining and work surface must be no higher than 34” above the floor.Lower the sink to the maximum height of 34" above the floor. Provide knee clearance underneath the counter at the sink that is a minimum of 11" deep at 9" above the floor and 8" deep at 27" above the floor. | 2000 | No | 8
3571 | Mobile Vendor Carts | Yes | The counters are 39" and 35" above the ground. | §904.4.1 | A portion of the service counter must be no higher than 36" above the floor for a horizontal distance of 36". | 2000 | No | 8
3044 | Zoo Kitchen | Yes | The sink is 36" above the floor. The dining and work surface counter is 36" above the floor.There is no knee clearance underneath the sink. | §306.3.3, §902.3, §606.3 | Provide knee clearance underneath the counter at the sink that is a minimum of 11" deep at 9" above the floor and 8" deep at 27" above the floor.Although not a public use area, should an employee with a disability request it, a sink and counter no higher than 34" should be provided. | 2000 | No | 8
3493 | Main Entrance Parking Adjacent to Park | Yes | The painted lines for the accessible parking spaces are faded. | §502 | Restripe and repaint the accessible parking spaces, access aisles, and ISA symbols. | 2000 | No | 9
2346 | Bench | Yes | The clear floor space has a 5.7% slope. | §305.2 | For the purposes of achieving greater accessibility and Human Centric Design, reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 0
2324 | Central Paving Entry Bridge Bench | Yes | The clear floor space has a 9.3% slope. | §305.2 | For the purposes of achieving greater accessibility and Human Centric Design, reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 0
2330 | Serval Cat | Yes | The clear floor space has a 3.2% slope. | §305.2 | For the purposes of achieving greater accessibility and Human Centric Design, reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions or relocate the bench to an area adjacent to a level 30"x48" c | 2500 | No | 0
3677 | South American Loop | Yes | The ramp has a 13.9% cross slope in front of the Coati. | §405.3 | Reconstruct the ramp to have a cross slope of 2% or less. | 2500 | No | 1
3233 | African Ranger Station | Yes | The running slope is 6%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5%. | 2500 | No | 3
3218 | Ant Eater Exit | Yes | The running slope is 7.7%. | §403.3 | Or install handrails at a minimum height of 34” and maximum of 38” above the ground. Make sure there are adequate handrail extensions and level landings at the top and bottom of the handrail.Reconstruct the route to reduce the running slope to a maximum of 5%. | 2500 | No | 3
2338 | Bat House Entrance | Yes | The entrance has a 4.2% slope. | §404.2.4.4 | Reconstruct the entryway to reduce the running slope to a maximum of 2% in all directions for a distance of 60" perpendicular to the door. | 2500 | No | 3
3171 | Bird Holding Door B | Yes | The entrance has a 9% to 10% slope. | §404.2.4.4 | Reconstruct the entryway to reduce the running slope to a maximum of 2% in all directions for a distance of 60" perpendicular to the door. | 2500 | No | 3
3075 | Butterfly House | Yes | The cross slope is 6.8%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
2325 | Central Paving Entry Bridge | Yes | There are no handrails.The running slope of the ramp is 11.1%. | §405.2, §505.2 | Reconstruct the ramp to reduce the running slope to a maximum of 8.3% or reconstruct the ramp to have a maximum slope of 5% with no handrails or level landings.Install handrails at a minimum height of 34” and maximum of 38” above the ground. Make sure there are adequate handrail extensions both at the top and bottom of the handrail. | 2500 | No | 3
3509 | Conservation Cruise | Yes | The running slope at the Conservation Cruise bridge is 7.9%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5% or install handrails and level landings. | 2500 | No | 3
3710 | Education Building | Yes | The turning space leaving the education building has an 8% slope. | §304.2 | Reconstruct the turning space to reduce the slope to the maximum allowable 2% in all directions for a duration of at least 60". | 2500 | No | 3
2361 | Education Building towards Zoo Kitchen | Yes | The running slope reaches 12.1%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5% or 8.3% with handrails and level landings. | 2500 | No | 3
3755 | Farm Animals Exhibit | Yes | The running slope is 9.5% and the cross slope is 10%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2% and a maximum running slope of 5%. | 2500 | No | 3
3354 | Giraffes Viewing | Yes | The turning space has a 12% slope.There is not a level landing at the bottom of the ramp. | §405.7, §304.2 | Install a level landing at the bottom of the ramp. Landings shall be as wide as the widest ramp run leading to the landing and 60" long minimum.Reconstruct the turning space to reduce the slope to the maximum of 2% in all directions. | 2500 | No | 3
3389 | Giraffes Viewing | Yes | The cross slope is 5%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3543 | Giraffes Viewing | Yes | The cross slope is 4.5%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3595 | Giraffes Viewing | Yes | The cross slope is 10.5%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3759 | Giraffes Viewing | Yes | The landing has a 2.3% cross slope and 4.6% running slope. | §405.7.1 | Reconstruct the top landing to have a maximum slope of 2% in all directions. | 2500 | No | 3
2340 | Gorongosa Entrance at Southern Ground Hornbill | Yes | The clear floor space at the Southern Ground Hornbill viewing has a 5% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3388 | Horned Owl Exhibit | Yes | The clear floor space at the Horned Owl viewing has excessive running slopes. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3492 | Main Entrance Parking Adjacent to Park | Yes | There are no marked "Van accessible" spaces. | §208.2.4 | Add a “van accessible” parking sign at a minimum height of 60" above the ground.Install a 132" wide van accessible parking space for every six accessible parking spaces. Where a 96" wide accessible parking space is provided, a 96" wide access aisle can also be considered an accessible. | 2500 | No | 3
3633 | Main Entrance Tickets | Yes | The clear floor space has a 3.2% slope. | §305.2 | Reconstruct a minimum of 30"x48" clear floor space adjacent to the ticket booth to have a maximum slope of 2% in all directions. | 2500 | No | 3
2332 | Nagel Beverage Boardwalk | Yes | The cross slope is 3%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3166 | North Parking by Gate 1 | Yes | The landing has a 3% slope. | §405.7.1 | Reconstruct the top landing to have a maximum slope of 2% in all directions. | 2500 | No | 3
2343 | Olive Baboon Viewing | Yes | The clear floor space at the Olive Baboon viewing has a 4.1% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3708 | Parakeet | Yes | The cross slope is 5%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3415 | Parque Nacional da Gorongosa African Wild Dog Viewing | Yes | The turning space has a 3.5% to 3.8% slope. | §304.2 | Reconstruct the turning space to reduce the slope to the maximum allowable 2% in all directions. | 2500 | No | 3
3407 | Parque Nacional da Gorongosa Chitengo Camp | Yes | The cross slope is 6.9%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3570 | Parque Nacional da Gorongosa EO Wilson Research Center | Yes | The entrance has a 6.5% slope. | §404.2.4.4 | Reconstruct the entryway to reduce the running slope to a maximum of 2% in all directions for a distance of 60" perpendicular to the doorway. | 2500 | No | 3
3002 | Parque Nacional da Gorongosa Nyala | Yes | The clear floor space at the Nyala viewing has a 3.9% running slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3163 | Parque Nacional da Gorongosa Otters | Yes | The clear floor space at the Otters viewing has a 3.8% cross slope and 4.6% running slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3507 | Parque Nacional da Gorongosa Warthog | Yes | The clear floor space for the Warthog viewing area has a 10.5% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3754 | Parque Nacional da Gorongosa Zebra | Yes | The clear floor space at the Zebra viewing has a 10% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
2367 | Path to Sloth Bear Viewing | Yes | The cross slope reaches 5.5%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3650 | Peregrine Exhibit | Yes | The clear floor space at the Peregrine viewing has a 4.3% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3214 | Red Panda Play Area | Yes | The turning space has a 3.5% slope. | §304.2 | Reconstruct the turning space to reduce the slope to the maximum allowable 2% in all directions. | 2500 | No | 3
2336 | Route from Penguin House Towards Nyala Exhibit | Yes | The recessed paw prints are a tripping hazard due to them being recessed up to 0.5".The running slope is 8%. | §403.3, §303.3 | Reconstruct the route to reduce the running slope to a maximum of 5%.Fill in the paw prints as to not exceed 0.25" in depth. | 2500 | No | 3
2876 | Sarus Crane | Yes | The clear floor space has a 3.5% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
2878 | Sarus Crane Indoor Viewing | Yes | The clear floor space at the Sarus Crane viewing has a 3.1% running slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3164 | Sloth Bear | Yes | The running slope is 12.6%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5% or 8.3% slope with level landings and handrails. | 2500 | No | 3
3418 | Sloth Bear | Yes | The running slope is 11.2%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5% or 8.3% slope with level landings and handrails. | 2500 | No | 3
3500 | Sloth Bear | Yes | The clear floor space at the Sloth Bear viewing has a 3.6% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3679 | Sloth Bear | Yes | The cross slope leading to the Sloth Bear is 5.5%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3032 | Sloth Bear Viewing Area Exit Ramp | Yes | The running slope of the ramp exiting the Sloth Bear viewing area is 12.5%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5% or 8.3% slope with level landings and handrails. | 2500 | No | 3
3018 | Small Animal Kingdom (SAK) | Yes | The clear floor space has a 4% slope. | §305.2 | For the purposes of achieving greater accessibility and Human Centric Design, reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions or relocate the bench to an area adjacent to a level 30"x48" c | 2500 | No | 3
3763 | Small Animal Kingdom (SAK) | Yes | The turning space has a 3.8% slope. | §304.2 | Reconstruct the turning space to reduce the slope to the maximum allowable 2% in all directions. | 2500 | No | 3
2382 | Small Animal Kingdom (SAK) - Gila Monster | Yes | The clear floor space has a 5.8% running slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
2376 | Small Animal Kingdom (SAK) - Path Leaving Rain Forest | Yes | The cross slope is 6.1%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
2380 | Small Animal Kingdom (SAK) - Rain Forest Entrance | Yes | The entrance has a 5.5% running slope and 4.3% cross slope. | §404.2.4.4 | Reconstruct the entryway to reduce the running slope to a maximum of 2% in all directions for a distance of 60" perpendicular to the doorway. | 2500 | No | 3
3221 | Small Animal Kingdom (SAK) Green Slide | Yes | The turning space has a 3.7% slope. | §304.2 | Reconstruct the turning space to reduce the slope to the maximum allowable 2% in all directions. | 2500 | No | 3
3125 | Small Animal Kingdom (SAK) Komodo Dragon | Yes | The clear floor space at the Komodo Dragon viewing has a 3.3% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3551 | Small Animal Kingdom (SAK) Lemur | Yes | The clear floor space at the Lemur viewing has a 3.9% to 5%. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3182 | Small Animal Kingdom (SAK) Rainforest Exit/Tiger Exhibit | Yes | The cross slope is 4.9%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3431 | Small Animal Kingdom (SAK) Rainforest Exit/Tiger Exhibit | Yes | There is not a firm, stable, and slip resistant route to the bench. | §302.1, §305 | For the purposes of achieving greater accessibility and Human Centric Design, construct a 30"x48" clear floor space to have a maximum slope of 2% in all directions or relocate the bench to an area adjacent to a level 30"x48" clear | 2500 | No | 3
3649 | Small Animal Kingdom (SAK) Rosy Boa | Yes | The clear floor space at the Rosy Boa has a 3.2% slope. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3360 | Small Animal Kingdom (SAK) Slender Tailed Meerkat | Yes | The cross slope is 3.1%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2% | 2500 | No | 3
2887 | Snow Leopard Viewing | Yes | The clear floor space at the Snow Leopard viewing has a running slope between 3% and 6%. | §305.2 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 3
3409 | South American Loop Capybara to Penguin Pavilion | Yes | The top landing has a 3.5% slope. | §405.7.1 | Reconstruct the top landing to have a maximum slope of 2% in all directions. | 2500 | No | 3
2855 | Temporary Exit | Yes | The running slope is 8%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5% or install handrails and ensure level landings are present. | 2500 | No | 3
3231 | Tiger Exhibit | Yes | The cross slope is 6.4%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3707 | Tiger Exhibit | Yes | The cross slope is 10%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 2500 | No | 3
3170 | Education Building Men’s Restroom by Condor Exhibit | Yes | There is not adequate maneuvering clearance to operate the door as the hallway is 40" wide. | §404.2.4.1 | Change the direction that the door swings or expand the area for which the door opens by removing obstructions to provide adequate maneuvering clearance of 60" perpedicular to the doorway. | 2500 | No | 4
3122 | Education Building Women’s Restroom by Condor Exhibit | Yes | There is not adequate maneuvering clearance to operate the door as the hallway is 40" wide. | §404.2.4.1 | Change the direction that the door swings or expand the area for which the door opens by removing obstructions to provide adequate maneuvering clearance of 60" perpedicular to the doorway. | 2500 | No | 4
2996 | EO Wilson Science and Exhibit Hall Men's Restroom | Yes | There is not adequate maneuvering clearance to operate the door at 47" wide. The FDC pipe is 11" deep protruding into the maneuvering clearance. | §404.2.4.1 | Change the direction that the door swings or expand the area for which the door opens by removing obstructions to provide adequate maneuvering clearance of 60" perpedicular to the doorway. | 2500 | No | 4
4492 | Small Animal Kingdom (SAK) Green Slide | Yes | The stairs do not have a transfer platform and are therefore not accessible to wheelchair users. | §1008.3.1.2 | The addition of a transfer platform of 14"x24" with a 30"x48" clear floor space is required. However, the addition of more accessible play equipment would be beneficial. | 2500 | No | 4
3662 | Education Building | Yes | The accessible water closet does not have a vertical grab bar.There are no grab bars. | §604.5, ICC A117.1 §604.5.1 | Install a side and rear grab bar at a minimum height of 33” and maximum height of 36” above the finish floor. The side grab bar shall have a minimum length of 42”. The side grab bar shall begin at a maximum of 12” from the back wall.Install an 18" long (minimum) vertical grab bar on the side wall. The grab bar shall be mounted with the bottom located at 39" minimum and 41" maximum above the floor. | 2500 | No | 5
3652 | Farm Animals Exhibit Stairs | Yes | The handrails are not continuous for the full length of each flight of stairs. | §505.3 | Extend the handrails to be continuous for the full length of each flight of stairs. | 2500 | No | 5
3260 | Men's Restroom by Condor Exhibit | Yes | There is not an accessible stall in the Men's Restroom by Condor Exhibit. | §213.3.1, §604.8.1.1 | Remount the toilet so the flush control is on the open side of the wall. Mount compliant grab bars.Either expand the toilet compartment or make the restroom a single-use stall so that the accessible stall is a minimum of 60" wide and 59" deep. | 2500 | No | 5
3219 | Small Animal Kingdom (SAK) Green Slide | Yes | There are no handrail extensions at the top and bottom of the stairs.There is a handrail on one side. | §505.2, §505.10.2, §505.10.3 | Install an additional handrail at a minimum height of 34” and maximum of 38” above the ground. Handrail extensions shall return to the guard or landing surface.Install new handrails that have extensions at the slope of the stair flight for a horizontal distance at least equal to one tread depth beyond the last riser nosing. | 2500 | No | 5
3515 | African Ranger Station Jeep Bat Eared fox | Yes | The clear floor space adjacent to the garbage can has a 3.3% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions or relocate the garbage can to a level location. | 2500 | No | 7
3080 | Carousel | Yes | The carousel is only accessible via a 7" step. | §405 | Add vertical access to the amenity via a movable ramp. If a ramp is added, ensure that the slope does not exceed 8.3%, handrails are provided, and there is sufficient room for a level landing at the top and bottom of the ramp. | 2500 | No | 7
2347 | Garbage Can Across from Zoo Kitchen | Yes | The clear floor space to the garbage can has a 5% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions or relocate the garbage can to a level area. | 2500 | No | 7
2341 | Garbage Can at Gorongosa Entrance Across From Southern Ground Hornbill | Yes | The clear floor space to the garbage can has a 5% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions or relocate the garbage can to a level area. | 2500 | No | 7
3589 | Garbage Can at Sloth Bear Exhibit | Yes | The clear floor space has a 6% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions or relocate the garbage can to a level area. | 2500 | No | 7
2333 | Garbage Cans Across from Giraffe House | Yes | The clear floor space to the garbage cans has a 5.5% to 8.7% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions or relocate the garbage cans adjacent to a level area. | 2500 | No | 7
3101 | Giraffe Slide | Yes | The clear floor space has a 5.4% slope and is not a full 30"x48". | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 7
3350 | Giraffes Viewing | Yes | The running slope of the ramp is 9.4%. | §405.2 | Reconstruct the ramp to reduce the running slope to a maximum of 8.3%. | 2500 | No | 7
3719 | Kinkajou South American Loop | Yes | The elevated viewing window is only accessible via a 1.5" step.The clear floor space at the exhibit's viewing window has a 2.5% slope. | §305.2, §405 | Reconstruct a minimum of a 30"x48" clear floor space to have a maximum slope of 2% in all directions.Reconstruct the cement pad adjacent to the viewing window so it is flush with the surrounding ground and has a maximum of a 2% slope in all directions. | 2500 | No | 7
3732 | Main Entrance Parking Gate 9 | Yes | The running slope of the curb ramp is 9.2%. | §405.2 | Reconstruct the curb ramp to reduce the running slope to a maximum of 8.3%. | 2500 | No | 7
3167 | North Parking by Gate 1 | Yes | The running slope of the curb ramp is 10.8%. | §405.2 | Reconstruct the curb ramp to reduce the running slope to a maximum of 8.3%. | 2500 | No | 7
3314 | Ramp to Bear Viewing | Yes | The clear floor space has a 4.3% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 7
2360 | Recycling Cans near Zoo Kitchen | Yes | The clear floor space has a 3.2% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 7
3532 | South American Loop Penguin Pavilion | Yes | The clear floor space has a 4.2% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 7
2345 | Trash Can Across from Carousel | Yes | The clear floor space in front of the garbage can has a 8% slope. | §305.2 | Reconstruct the 30"x48" clear floor space to have a maximum slope of 2% in all directions. | 2500 | No | 7
3572 | African Ranger Station Jeep | Yes | The elevated component is only accessible a 2' step up. | §405 | Consider adding vertical access to this play component or adding an additional play component that can be accessed from ground level. | 2500 | No | 8
2326 | Lions Pathway | Yes | The running slope reaches 9%. | §403.3 | Reconstruct the route to reduce the running slope to a maximum of 5% or 8.3% if handrails are level landings are provided. | 3000 | No | 3
2342 | EO Wilson Science and Exhibit Hall | Yes | The interactive touch screen does not have any sound or tactile components. Therefore, a visually impaired person would not be able to access the information provided by the kiosk. | §707 | Audio instructions must be provided that guide the user through all the functions of the machine. Tactile instructions must be provided informing the user on the method of activating the audio instructions. | 3000 | No | 8
2337 | Penguin House | Yes | The coin slot is outside of the unobstructed forward reach range at 52" above the floor. | §308.2.1 | This may require replacing the machine.Lower the coin slot by 4" to meet the accessible reach range of 48" maximum above the floor. | 3000 | No | 8
3145 | Main Entrance Parking Adjacent to Park | Yes | The running slope of the curb ramp is 10%.There is no landing provided at the top of the curb ramp. | §406.4, §405.2 | Install a landing at the top of the curb ramp with a minimum clear length of 36" or reconstruct the ramp as a parallel curb ramp.Reconstruct the curb ramp to reduce the running slope to a maximum of 8.3%. | 3500 | No | 3
3582 | Orangutan Path | Yes | There is a 2" gap in the walkway.The turning space has a 13.2% slope. | §304.2, §302.3 | Reconstruct the turning space to reduce the slope to the maximum allowable 2% in all directions.Fill in the gap to reduce the gap to a maximum of 0.5" in width. | 3500 | No | 3
3377 | South American Loop Penguin Pavilion | Yes | The active leaf does not have a clear opening width of 32".The elevated component is only accessible via a 5" step. | §405, §404.2.2 | Add vertical access to the amenity via a ramp. If a ramp is added, ensure that the slope does not exceed 8.3%, handrails are provided, and there is sufficient room for a level landing at the top and bottom of the ramp.Expand the opening width of the active leaf to ensure a clear opening width of greater than 32". | 4000 | No | 0
3733 | Main Entrance Gate 1 Boutique Gift Shop | Yes | The cross slope is 7.6%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 4000 | No | 3
3300 | Ramp to Bear Viewing | Yes | The cross slope is 7.6%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 4000 | No | 3
3427 | Small Animal Kingdom (SAK) Rainforest Exit | Yes | The provided picnic table does not have an accessible clear space for a wheelchair user.There is not a firm, stable, and slip resistant route to the picnic table. | §302.1, §305, §226.1, §902, §306 | Ensure that the wheelchair accessible seating has a clear floor space of 30" x 48" with a slope not steeper than 2% and that the tables have sufficient knee and toe clearance.Add/replace picnic tables so that at least 5% of the seating is wheelchair accessible. Construct a firm, stable, and slip resistant accessible route with a maximum cross slope of 2% and maximum running slope of 5%. | 4000 | No | 3
2874 | Soala Viewing | Yes | There are not level landings at the top and bottom of the ramp on either side. | §405.7 | Install level landings at the top and bottom of the ramp. Landings shall be as wide as the widest ramp run leading to the landing and 60" long minimum. | 4000 | No | 3
2882 | Stage | Yes | The running slope at the top of the ramp is 9.5%. | §405.2 | Reconstruct the top of the ramp to reduce the running slope to a maximum of 8.3%. | 4000 | No | 3
2998 | Parque Nacional da Gorongosa Zebra | Yes | There are no handrails, even though the ramp has a running slope of up to 7.5%. | §505.2 | Install handrails at a minimum height of 34” and maximum of 38” above the ground. Make sure there are adequate handrail extensions both at the top and bottom of the handrail. | 4000 | No | 6
2372 | Pupil Room - Butterfly Sanctuary | Yes | The elevated component is only accessible via a step. | §405 | Add vertical access to the amenity via a ramp. If a ramp is added, ensure that the slope does not exceed 8.3%, handrails are provided, and there is sufficient room for a level landing at the top and bottom of the ramp. | 4000 | No | 7
2872 | African Plains Exhibit Animal Presentation Area | Yes | Across the pathway, there is a 3% cross slope. | §403.3 | Resurface the route to reduce the cross slope to a maximum of 2%. | 5000 | No | 3
2365 | Education Building Entrance | Yes | The entrance has a 12.7% slope. | §404.2.4.4 | Leading to the door, ensure that the running slope does not exceed 5% or 8.3% if handrails and level landings are provided.Reconstruct the entryway to reduce the running slope to a maximum of 2% in all directions for a distance of 60" perpendicular to the door. | 5000 | No | 3
3454 | Giraffe Slide | Yes | The giraffe slide is not accessible. There are changes in level that pose tripping hazards on the route to the giraffe slide.The playground surface is not stable, firm, and slip resistant. | §302.1, ASTM F1951-99 | Replace the mulch with an accessible playground surface material such as pour-in-place rubber, rubber tiles, artificial grass, and engineered wood fiber.Install an accessible play element in addition to the giraffe slide. Repave the area of the sidewalk to remove the change in level. | 5000 | No | 3
3416 | Main Entrance Gate 1 Boutique Gift Shop | Yes | The entrance to the boutique gift shop has a 8.8% slope. | §404.2.4.4 | Leading to the door, ensure that the running slope does not exceed 5% or 8.3% if handrails and level landings are provided.Reconstruct the entryway to reduce the running slope to a maximum of 2% in all directions for a distance of 60" perpendicular to the door. | 5000 | No | 3
3469 | Main Entrance Parking Gate 1 | No | The parking spaces have a running slope between 3% and 4%.There are no marked "Van Accessible" spaces as existing accessible spaces are 77", 94", and 97" wide. | §208.2.4, §502.4 | Where a 96" wide accessible parking space is provided, a 96" wide access aisle can also be considered an accessible. Add a “van accessible” parking sign at a minimum height of 60" above the ground.Resurface the parking spaces to reduce the slope to a maximum of 2% in all directions. Install a 132" wide van accessible parking space for every six accessible parking spaces. | 5000 | No | 3
3578 | Main Entrance Parking Gate 10 | Yes | The parking spaces and access aisle have a 3.3% running slope.One of the accessible parking space is not of sufficient width at 88" wide. | §502.2, §502.4 | Expand the accessible parking space to be a minimum width of 96", or 132" if designated as a van accessible parking space. Ensure the adjacent access aisle remains 60" wide.Resurface the parking spaces and access aisles to reduce the slope to a maximum of 2% in all directions. | 5000 | No | 3
2327 | Nagel Beverage Boardwalk | Yes | The cross slope is 15%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 5000 | No | 3
3154 | Orangutan Path | Yes | The running slope reaches 8.4%. | §403.3 | Either resurface the path to ensure the running slope does not exceed 8.3%, install handrails, and level landings. Or reconstruct the route to have a maximum running slope of 5%. | 5000 | No | 3
3095 | Parque Nacional da Gorongosa | Yes | The cross slope ranges from 2.7% to 4.1%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2% and a maximum running slope of 5%. | 5000 | No | 3
3305 | Parque Nacional da Gorongosa Chitengo Camp | Yes | There is not a firm, stable, and slip resistant route to the Chitengo Camp tents. | §302.1, §305 | Ensure that the running slope is a maximum of 5% and the cross slope is a maximum of 2% so that, a minimum of 5% tents are accessible.Replace the mulch with a firm, stable, and slip resistant surface, such as engineered wood fiber. | 5000 | No | 3
3237 | Red Panda Exhibit Class Area | Yes | There is not a firm, stable, and slip resistant route to the picnic tables.The elevated component is only accessible via stairs. | §405, §302.1, §305 | Add vertical access to the amenity. If a ramp is added, ensure that the slope does not exceed 8.3%, handrails are provided, and there is sufficient room for a level landing at the top and bottom of the ramp.Construct a firm, stable, and slip resistant accessible route with a maximum cross slope of 2% and maximum running slope of 5%. | 5000 | No | 3
3280 | Red Panda Play Area | Yes | The play area surface is not stable, firm, and slip resistant. | ASTM F1951-99 | Replace the mulch with an accessible playground surface material such as pour-in-place rubber, rubber tiles, artificial grass, or engineered wood fiber. | 5000 | No | 3
2879 | Seating Area | Yes | The provided picnic tables do not have accessible clear spaces for a wheelchair user. | §226.1, §902, §305, §306 | Ensure that the wheelchair accessible seating has a clear floor space of 30" x 48" with a slope not steeper than 2% and that the tables have sufficient knee and toe clearance.Add/replace picnic tables so that at least 5% of the seating is wheelchair accessible. | 5000 | No | 3
3303 | Small Animal Kingdom (SAK) Playground | Yes | The playground surface is not stable, firm, and slip resistant. | ASTM F1951-99 | Replace the mulch with an accessible playground surface material such as pour-in-place rubber, rubber tiles, artificial grass, or engineered wood fiber. | 5000 | No | 3
3425 | Small Animal Kingdom (SAK) Rainforest Exit/Tiger Exhibit | Yes | The running slope of the wood bridge at the beginning is 10% and the ranges from 5.5% to 7%. | §403.3 | Reconstruct the entrance to the bridge to ensure that the slope does not exceed 8.3%. Add handrails and edge protection on the bridge and ensure that there are level landings on both sides. | 5000 | No | 3
3068 | Education Building Women’s Restroom | Yes | There is not an accessible stall in the Education Building Women’s Restroom at 57" deep and 30" wide. | §213.3.1, §604.8.2.1 | Expand the restroom to ensure 60" minimum measured perpendicular from the side wall and 56" minimum measured perpendicular from the rear wall. | 5000 | No | 5
3220 | Small Animal Kingdom (SAK) Green Slide | Yes | Open risers are not permitted. | §504.3 | Replace the stairs to ensure that the risers are closed. | 5000 | No | 5
3559 | Zoo Kitchen Restroom | Yes | The side grab bar is located more than 12" from the rear wall. | §604.5.1 | Build out the sidewall to ensure that no sections are projecting out into the restroom. | 5000 | No | 5
3697 | Animal Care Staff Break/Office Area Ramp to Lunch Area | Yes | The running slope of the ramp is between 8% and 9%. | §405.2 | Reconstruct the ramp to reduce the running slope to a maximum of 8.3%. | 5000 | No | 7
2344 | Benches at Gorongosa Entrance | Yes | There is no clear floor space next to the benches. | §903.2 | For the purposes of achieving greater accessibility and Human Centric Design, install a 30"x48" clear floor space at the end of the bench seats and parallel to the short axis of the benches. | 5000 | No | 8
2873 | Meeting Area | Yes | The meeting area under the tent is only accessible via a 2.5" step and via a dirt and mulch surface. | §405 | Add a curb ramp with a slope not exceeding 8.3%. Ensure there is a level landing at the top of the curb. Ensure the path leading to and within the tent is made from a firm, stable, and slip resistant material. | 7500 | No | 3
2997 | Parque Nacional da Gorongosa Zebra | Yes | The cross slope is 3%. | §403.3 | Reconstruct the route to reduce the cross slope to a maximum of 2%. | 7500 | No | 3
3104 | Ramp to Bear Viewing | Yes | There are no handrails.The running slope of the ramp is 9.6%. The cross slope of the ramp is 2.6%. | §405.2, §405.3, §505.2 | Reconstruct the path to ensure that the cross slope does not exceed 2%. The running slope must not exceed 8.3% and have level landings and handrails mounted between 34" and 38" above the ground. | 10000 | No | 3
3671 | Ramp to Bear Viewing | Yes | A section of the pavement is uneven posing a tripping hazard and causing a running slope of 12.3%. | §403.3, §302.1 | Reconstruct the pathway to ensure that the uneven section of asphalt is level, with vertical changes in elevation not exceeding 0.25". | 10000 | No | 3
3380 | Red Panda Exhibit | Yes | The Red Panda exhibit viewing area is not a firm, stable, and slip resistant surface and contains cross slope of up to 3.5%. | §302.1 | Pave the viewing area with a stable, firm, and slip resistant surface ensuring that it has compliant running and cross slopes. | 10000 | No | 3
3501 | Entire Facility | Yes | There is no tactile signs identifying 190 permanent rooms. | §216.2, §703 | Signs shall be Braille with raised lettering and should be placed on the wall in the center of an 18"x18" clear floor space.Install tactile signage on the latch side of all the doorways, leading to permanent rooms or places, at a height of 48” minimum to 60” maximum above the floor, identifying the room by name or room number. | 19000 | No | 3
High (1-4) | 362100
Medium (5-7) | 148000
Low (8-10) | 48700
Total | 558800
Quick Fix | 12300